## Month 1
Day | Week | Date | Day | Hrs Planned | Activity Planned | Asignee | Status in % | Remark
1 | 1 | 2021-01-21 | Thursday | 3 | Design Library for keypad interfacing Contact BMS Vendors get the quotes Order CAN analyzer | Akshay Parag Parag | 100 | Keypad Libraries Tested: First Level Demo shown CAN analyser ordered: From DigiKey BMS Vendor from Pune finalized : SSK
2 |  | 2021-01-22 | Friday | 3
3 |  | 2021-01-23 | Saturday | 0 | Work on remaining Task
4 |  | 2021-01-24 | Sunday | 0
5 |  | 2021-01-25 | Monday | 3 | Design Library for LCD messages for each mode Contact BMS Vendors get the quotes Design Zero PCB board for Embedded Systems | Akshay Parag Parag | 100 | Battery Pack and BMS vendor finalized Quote approved on 08-02-2021 LCD libraries tested successfully
6 |  | 2021-01-26 | Tuesday | 3
7 |  | 2021-01-27 | Wednesday | 3
8 | 2 | 2021-01-28 | Thursday | 3
9 |  | 2021-01-29 | Friday | 3
10 |  | 2021-01-30 | Saturday | 0 | Work on remaining Task
11 |  | 2021-01-31 | Sunday | 0
12 |  | 2021-02-01 | Monday | 3 | Design Firmware for each mode Test Keypad and LCD Libraries for each mode Design Schematic for Embedded System Place Order of BMS and Battery Pack (P0) | Akshay Parag Parag Parag | 100 | RTOS Based Firmware designed for each mode and tested ADD_Credits and other logics like Charging/ Credits expired Design Layout activity on going waiting for component availability confirmation from vendor
13 |  | 2021-02-02 | Tuesday | 3
14 |  | 2021-02-03 | Wednesday | 3
15 | 3 | 2021-02-04 | Thursday | 3
16 |  | 2021-02-05 | Friday | 3
17 |  | 2021-02-06 | Saturday | 0 | Work on remaining Task
18 |  | 2021-02-07 | Sunday | 0
19 |  | 2021-02-08 | Monday | 3 | Integrate All the tested libraries of keypad & LCD Test them for longer run Design Layout of Embedded System and place order asap | Akshay Parag Parag | 100 | Embedded system components ordered based on availability in local market Checking in local market took time
20 |  | 2021-02-09 | Tuesday | 3
21 |  | 2021-02-10 | Wednesday | 3
22 | 4 | 2021-02-11 | Thursday | 3
23 |  | 2021-02-12 | Friday | 3
24 |  | 2021-02-13 | Saturday | 0 | Work on remaining Task
25 |  | 2021-02-14 | Sunday | 0
26 |  | 2021-02-15 | Monday | 3 | Test the source code and all the testcases on new designed PCB and work on the issues Test CAN data of Battery pack sent by BMS | Akshay Parag Parag | 100 | Worked on few issues of LCD for printing on different lines Worked to generate simulated CAN data with CAN Analyzer and successfully receive it on the ES We were able to print this simulated CAN data
27 |  | 2021-02-16 | Tuesday | 3
28 |  | 2021-02-17 | Wednesday | 3
29 | 5 | 2021-02-18 | Thursday | 3
30 |  | 2021-02-19 | Friday | 3
31 |  | 2021-02-20 | Saturday | 0 | Work on remaining Task
32 |  | 2021-02-21 | Sunday | 0
After 32 Days |  |  | Total Hrs | 66 | At the end of 1st Month Embedded System will be tested OK Also BMS and Battery pack are in hand before 15-02-2021
Cost per hr : 850 Rs |  |  | Total Engineering Cost | 56100 | Paid Amount | 20000 | Balance | 36100

## Month 2
Day | Week | Date | Day | Hrs Planned | Activity Planned | Asignee | Status in % | Remark
1 | 1 | 2021-06-21 | Monday | 3 | Design The CAN libraries for controller Design Unit Test Case matching with Requirements Design Contactor circuitary and test it | Akshay Parag Parag | 100 | Tested Contactor circuitary Tested Dev board integration with CAN libraries with BMS CAN data output
2 |  | 2021-06-22 | Tuesday | 3
3 |  | 2021-06-23 | Wednesday | 3
4 |  | 2021-06-24 | Thursday | 3
5 |  | 2021-06-25 | Friday | 3
6 |  | 2021-06-26 | Saturday | 0 | Work on Remaining Tasks
7 |  | 2021-06-27 | Sunday | 0
8 | 2 | 2021-06-28 | Monday | 3 | Design code to receive each message from BMS over CAN and update the corresponding stats Design Contactor circuitary schematic and Layout | Akshay Parag | 100 | Code designed and tested for updation of parameters Working as expected Layout designed
9 |  | 2021-06-29 | Tuesday | 3
10 |  | 2021-06-30 | Wednesday | 3
11 |  | 2021-07-01 | Thursday | 3
12 |  | 2021-07-02 | Friday | 3
13 |  | 2021-07-03 | Saturday | 0 | Work on Remaining Tasks
14 |  | 2021-07-04 | Sunday | 0
15 | 3 | 2021-07-05 | Monday | 3 | Integrate all the code and unit test the code Test all the unit tests designed by Parag for this project | Akshay Parag | 100 | Integrateed both logics 1. Tested all the data received updates parameter 2. Tested if load disconnects after credits are overed.
16 |  | 2021-07-06 | Tuesday | 3
17 |  | 2021-07-07 | Wednesday | 3
18 |  | 2021-07-08 | Thursday | 3
19 |  | 2021-07-09 | Friday | 3
20 |  | 2021-07-10 | Saturday | 0 | Work on Remaining Tasks
21 |  | 2021-07-11 | Sunday | 0
22 | 4 | 2021-07-12 | Monday | 3 | All Long Run tests for ex. 1) Charging Updates on LCD 2) Discharging updates in credits 3) Credits over and contactor control | Akshay & Parag | 100 | 1. Tested for half battery Capacity 2. Tested for full battery charge 3. Tested for small amount of credits left
23 |  | 2021-07-13 | Tuesday | 3
24 |  | 2021-07-14 | Wednesday | 3
25 |  | 2021-07-15 | Thursday | 3
26 |  | 2021-07-16 | Friday | 3
27 |  | 2021-07-17 | Saturday | 0 | Work on Remaining Tasks
28 |  | 2021-07-18 | Sunday | 0
After 28 Days |  |  | Total Hrs | 60 | At the end of 2nd Month Embedded System will be tested OK with Battery pack and BMS Integrated
Cost per hr : 850 Rs |  |  | Total Engineering Cost | 51000 | Paid Amount | 0 | Balance | 51000
Battery pack delivered on 21-June-21 Due to heavy lockdown measures in Maharashtra
Apart from above activities we have worked on packaging of the device to help customer showcase it better way