## Month 1
Day | Week | Date | Day | Hrs Planned | Activity Planned | Asignee | Status in % | Remark
1 | 1 | 2021-01-21 | Thursday | 3 | Design Library for keypad interfacing Contact BMS Vendors get the quotes Order CAN analyzer | Akshay Parag Parag | 100 | Keypad Libraries Tested: First Level Demo shown CAN analyser ordered: From DigiKey BMS Vendor from Pune finalized : SSK
2 |  | 2021-01-22 | Friday | 3
3 |  | 2021-01-23 | Saturday | 0 | Work on remaining Task
4 |  | 2021-01-24 | Sunday | 0
5 |  | 2021-01-25 | Monday | 3 | Design Library for LCD messages for each mode Contact BMS Vendors get the quotes Design Zero PCB board for Embedded Systems | Akshay Parag Parag
6 |  | 2021-01-26 | Tuesday | 3
7 |  | 2021-01-27 | Wednesday | 3
8 | 2 | 2021-01-28 | Thursday | 3
9 |  | 2021-01-29 | Friday | 3
10 |  | 2021-01-30 | Saturday | 0 | Work on remaining Task
11 |  | 2021-01-31 | Sunday | 0
12 |  | 2021-02-01 | Monday | 3 | Design Firmware for each mode Test Keypad and LCD Libraries for each mode Design Schematic for Embedded System Place Order of BMS and Battery Pack (P0) | Akshay Parag Parag Parag
13 |  | 2021-02-02 | Tuesday | 3
14 |  | 2021-02-03 | Wednesday | 3
15 | 3 | 2021-02-04 | Thursday | 3
16 |  | 2021-02-05 | Friday | 3
17 |  | 2021-02-06 | Saturday | 0 | Work on remaining Task
18 |  | 2021-02-07 | Sunday | 0
19 |  | 2021-02-08 | Monday | 3 | Integrate All the tested libraries of keypad & LCD Test them for longer run Design Layout of Embedded System and place order asap | Akshay Parag Parag
20 |  | 2021-02-09 | Tuesday | 3
21 |  | 2021-02-10 | Wednesday | 3
22 | 4 | 2021-02-11 | Thursday | 3
23 |  | 2021-02-12 | Friday | 3
24 |  | 2021-02-13 | Saturday | 0 | Work on remaining Task
25 |  | 2021-02-14 | Sunday | 0
26 |  | 2021-02-15 | Monday | 3 | Test the source code and all the testcases on new designed PCB and work on the issues Test CAN data of Battery pack sent by BMS | Akshay Parag Parag
27 |  | 2021-02-16 | Tuesday | 3
28 |  | 2021-02-17 | Wednesday | 3
29 | 5 | 2021-02-18 | Thursday | 3
30 |  | 2021-02-19 | Friday | 3
31 |  | 2021-02-20 | Saturday | 0 | Work on remaining Task
32 |  | 2021-02-21 | Sunday | 0
After 32 Days |  |  | Total Hrs | 66 | At the end of 1st Month Embedded System will be tested OK Also BMS and Battery pack are in hand before 15-02-2021
Cost per hr : 850 Rs |  |  | Total Engineering Cost | 56100 | Paid Amount | 20000 | Balance | 36100

## Month 2
Day | Week | Date | Day | Hrs Planned | Activity Planned | Asignee | Status in % | Remark
1 | 1 | 2021-03-02 | Monday | 3 | Design The CAN libraries for controller Design Unit Test Case matching with Requirements Design Contactor circuitary and test it | Akshay Parag Parag
2 |  | 2021-03-03 | Tuesday | 3
3 |  | 2021-03-04 | Wednesday | 3
4 |  | 2021-03-05 | Thursday | 3
5 |  | 2021-03-06 | Friday | 3
6 |  | 2021-03-07 | Saturday | 0 | Work on Remaining Tasks
7 |  | 2021-03-08 | Sunday | 0
8 | 2 | 2021-03-09 | Monday | 3 | Design code to receive each message from BMS over CAN and update the corresponding stats Design Contactor circuitary schematic and Layout | Akshay Parag
9 |  | 2021-03-10 | Tuesday | 3
10 |  | 2021-03-11 | Wednesday | 3
11 |  | 2021-03-12 | Thursday | 3
12 |  | 2021-03-13 | Friday | 3
13 |  | 2021-03-14 | Saturday | 0 | Work on Remaining Tasks
14 |  | 2021-03-15 | Sunday | 0
15 | 3 | 2021-03-16 | Monday | 3 | Integrate all the code and unit test the code Test all the unit tests designed by Parag for this project | Akshay Parag
16 |  | 2021-03-17 | Tuesday | 3
17 |  | 2021-03-18 | Wednesday | 3
18 |  | 2021-03-19 | Thursday | 3
19 |  | 2021-03-20 | Friday | 3
20 |  | 2021-03-21 | Saturday | 0 | Work on Remaining Tasks
21 |  | 2021-03-22 | Sunday | 0
22 | 4 | 2021-03-23 | Monday | 3 | All Long Run tests for ex. 1) Charging Updates on LCD 2) Discharging updates in credits 3) Credits over and contactor control | Akshay & Parag
23 |  | 2021-03-24 | Tuesday | 3
24 |  | 2021-03-25 | Wednesday | 3
25 |  | 2021-03-26 | Thursday | 3
26 |  | 2021-03-27 | Friday | 3
27 |  | 2021-03-28 | Saturday | 0 | Work on Remaining Tasks
28 |  | 2021-03-29 | Sunday | 0
After 28 Days |  |  | Total Hrs | 60 | At the end of 2nd Month Embedded System will be tested OK with Battery pack and BMS Integrated
Cost per hr : 850 Rs |  |  | Total Engineering Cost | 51000 | Paid Amount | 0 | Balance | 51000